## Sheet1
[7 empty] | Month 1 |  |  |  |  | Month 2 |  |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  |  | Month 5 |  |  |  |  | Month 6 |  |  |  |  | Month 7 |  |  |  |  | Month 8 |  |  |  |  | Month 9
Activity | Task | Detail | Assigned to | Due Date | Date Completed | Pre-Award | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5
1 |  | GOVERNANCE
| 1.1 | Pre-CRC Establishment
| 1.1.1 | Reserve CRC company names with ASIC | CEO, BM
| 1.1.2 | Reserve URL and Domain Names | CEO, BM
| 1.2 | Interim Establishment and Governance Arrangements
| 1.2.1 | Appoint Legal Advisor to assist with CRC establishment (approved by Interim Board) | CEO
| 1.2.2 | Legal Advisor provides draft Interim Constitution | Lawyer
| 1.2.3 | Appoint Interim Chair, Company Secretary and Independent Board Members | Interim Chair, CEO
| 1.2.4 | Reigster CRC company name with ASIC | Lawyer
| 1.2.5 | Apply for ABN and TFN | Lawyer
| 1.2.6 | Draft Interim Constitution | CEO
| 1.2.7 | Approve Interim Constitution | Interim Board
| 1.2.8 | Lodge Interim Constitution with ASIC | Lawyer
| 1.2.9 | Lodge Directors Consent to Act Notice | Lawyer or CoSec
| 1.2.10 | Company incorporated and communicated to Interim Board | BM
| 1.2.11 | Constitution and Certificate of Incorporated filed in Stat records | BM
| 1.3 | Constitution
| 1.3.1 | Draft Constitution amemdments to reflect full operations | Lawyer, CEO, Interim Chair
| 1.3.2 | Circulate Constitution to Partners/Members for comment | CEO, BM
| 1.3.3 | Review Member feedback | CEO, Interim Board
| 1.3.4 | Prepare final draft of Constitution for resolution at AGM | Lawyer, CEO
| 1.3.5 | Constitution lodged with ASIC / ACNC | CoSec
| 1.3.6 | Constitution and Certificate of Incorporation filed in Stat records | BM
| 1.4 | Partner Agreement
| 1.4.1 | Prepare Draft Partners Agreement | Lawyer, CEO
| 1.4.2 | Draft approved for circulation to partners | Interim Board
| 1.4.3 | Round 1 Draft Partner Agreement circulated to Partners for review and comment | BM
| 1.4.4 | Round 1 Partner comments reviewed, recommended changes incorporated or Partner Feedback response prepared | Lawyer, CEO
| 1.4.5 | Round 2 Draft Partner Agreement and Round 1 Feedback approved for circulation to partners | Interim Board
| 1.4.6 | Round 2 Draft Partner Agreement and Round 1 Feedback circulated to Partners for review and comment | BM
| 1.4.7 | Round 2 Participants comments reviewed, changes incorporated and Partner Feedback prepared | Lawyer, CEO
| 1.4.8 | Final Draft of Partner Agreement and Round 2 Feedback approved for circulation to partners | Interim Board
| 1.4.9 | Final Draft Partner Agreement and Round 2 Feedback circulated to Partners | Interim Board
| 1.4.10 | Partner Agreement Executed by all Participants | CEO
| 1.4.11 | Participants Agreement lodged with Commonwealth | BM
| 1.4.12 | Participants Agreement filed in Stat records. | BM
| 1.5 | Commonwealth Grant Agreement (CGA)
| 1.5.1 | Draft CGA reviewed | Lawyer, CEO, Interim Chair
| 1.5.2 | Amendments and Comments sent to Commonwealth for review | BM / CEO
| 1.5.3 | Revised CGA reviewed | Lawyer, CEO, Interim Chair
| 1.5.4 | Final draft of CGA approved by Interim Board | Interim Board
| 1.5.5 | Final execution version of CGA prepared by Commonwealth | CRC Program Team
| 1.5.6 | CGA signed and sent to Commonwealth | Interim Chair and Interim Director
| 1.5.7 | Fully executed CGA received from Commonwealth and filed in Stat records | BM
| 1.6 | Director Appointments
| 1.6.1 | Establish Nominations Committee | Interim Board
| 1.6.2 | Draft Board Remuneration Policy | Nominations Committee
| 1.6.3 | Approve Director Nominations process for communication to Members | Nominations Committee
| 1.6.4 | Interim Board approves Nominations process, Members comms and Board Remuneration | Interim Board
| 1.6.5 | Send Director Nominations Process to Members | Chair
| 1.6.6 | Director nominations reviewed and recommendations prepared | Nominations Committee
| 1.6.7 | Director appointees notified | Chair
| 1.6.8 | Director nominees complete consents to act and Fit and Proper Person Declarations | Nominees
| 1.6.9 | Members'approve Director / Company Secretary Nominations at AGM | Members
| 1.6.10 | Members' approve Board Remuneration at AGM | Members
| 1.6.11 | Directors details provided to ASIC / ACNC | CoSec
| 1.6.12 | Statutory Records updated | BM
| 1.7 | Member Contact Information
| 1.7.1 | Prepare a Member Consent form for eligible partners to become members | Lawyer, BM
| 1.7.2 | Entities agreeing to be Members provide signed Member Consent forms and contact details | Members
| 1.7.3 | Records updated with nominee details | BM
| 1.7.4 | Members invited to AGM | Chair
| 1.8 | Other Participant Representatives
| 1.8.1 | All Participants requested to advise of participant representatives | CEO, BM
| 1.8.2 | Records updated with rep contact details | BM
| 1.9 | Board Committee Establishment (after appointment at AGM)
| 1.9.1 | Board holds first meeting | CEO
| 1.9.2 | Board to agree and sign Board Charter | Chair
| 1.9.3 | Board to agree on establishment of Board Committees | Board
| 1.9.4 | Board to nominate membership of each Board Committee | Board
| 1.9.5 | Board to approve Committees' Charter and terms of reference | Board
| 1.9.6 | Nominated Committee members interviewed | Board
| 1.9.7 | Committees established | Board
| 1.9.8 | Committees hold first meetings | Committees
| 1.1 | Appointment of Auditor
| 1.10.1 | Identify potential company auditors | BM
| 1.10.2 | Prepare 'request for proposal' for audit services | BM, CEO, Chair
| 1.10.3 | Contact candidates to tender for audit. | BM
| 1.10.4 | Board to review responses | Board
| 1.10.5 | Interview preferred auditor | CEO
| 1.10.6 | Board to recommend appointment | Board
| 1.10.7 | Members approves appointment at AGM | BM
| 1.10.8 | Auditor notified of appointment | BM
| 1.10.9 | ASIC / ACNC notified of appointment | BM
| 1.10.10 | Agree and sign Auditors' terms and conditions of engagement | Chair, Director
2 |  | FINANCIAL MANAGEMENT
| 2.1 | Accounting Package
| 2.1.1 | Sign-up for Accounting Package (Xero, MYOB) | CFO, Finance Team
| 2.1.2 | Set-up General Ledger Chart of Accounts | CFO, Finance Team
| 2.1.3 | Draft Accounting principles and Policy for approval | CEO, CFO, Chair
| 2.1.4 | Accounting principles and Policy approved by Board | Board
| 2.2 | Bank Account
| 2.2.1 | Contact AAA rated banks for terms and conditions | BM
| 2.2.2 | Refer preferred institution to Board for approval | CEO, BM
| 2.2.3 | Board to approve Bank Appointment, signatories and financial limits | Board
| 2.2.4 | Establish Operating Account, and any bank accounts required) | CEO, BM
| 2.2.5 | Complete Account Establishment process in accordance with Bank requirements | BM
| 2.3 | Tax Matters
| 2.3.1 | Apply for Tax File Number (if not completed) | CFO, Finance Team
| 2.3.2 | Submit application for tax exempt status | CFO, Finance Team
| 2.3.3 | Register for | CFO, Finance Team
| a) | GST
| b) | FBT
| c) | PAYG
| d) | Payroll
| e) | Superannuation Payments System
| 2.4 | Budget
| 2.4.1 | Prepare Operating Budget for first financial year for board approval | CEO, CFO
| 2.4.2 | Board approve Operating Budget | Board
| 2.4.3 | Implement Operating Budget | CEO, CFO
3 |  | INSURANCES
| 3.1 | Contact insurance broker for rates on relevant insurances (ensuring any obligations in CGA are met) | CFO, BM
| a) | Public Liability
| b) | Management Liability
| c) | Professional Indemnity
| d) | Business Travel
| e) | Cyber
| f) | Other insurance
| 3.2 | Complete proposal forms | CFO, BM
| 3.3 | Board to approve insurance cover | Board
| 3.4 | Finalise cover | CFO, BM
| 3.5 | Register for WorkCover in applicable states | CFO, Finance Team
4 |  | AGREEMENTS
| 4.1 | Draft (or lawyers draft): | Lawyer, CEO, BM
| a) | Project Agreement for Partners & Participants
| b) | Research Project Agreement involving Students
| c) | Third Party Project Agreement
| d) | Consultancy Agreement
| e) | Non-Disclosure Agreement
| f) | Contract Research Agreement
| a) | Student Scholarship Agreement
| b) | Scholarship Operation Agreement for University Partners
| c) | Employment Agreement
| d) | Secondment Heads of Agreeement
| e) | Other Agreements as needed
| 4.2 | Board to approve agreements | Board
| 4.3 | Final templates prepared and shared with parties as needed | BM
| 4.4 | Executed Agreements to noted in Agreeemnt Register and filed in Stat records | BM
5 |  | EMPLOYMENT
| 5.1 | Develop CEO Position Description and KPI | Chair
| 5.2 | Board review CEO Position Description and KPIs and appointment of CEO | Board
| 5.3 | Develop Position Description Documents including KPIs | Hiring Manager
| 5.4 | Advertise (internally / externally) for agreed employment roles | BM
| 5.5 | Review applications | Hiring Manager
| 5.6 | Interview preferred candidates | Hiring Manager
| 5.7 | Agree employment terms | BM
| 5.8 | Provide new employee(s) with employment contracts or secondment agreements | BM
| 5.9 | Board to approve contracts and job descriptions or delegate to relevant committee or Management | Board
| 5.1 | Recommend appointment for approval according to delegation | Hiring Manager
| 5.11 | Employees to sign new contracts | Employee
| 5.12 | Develop onboarding and induction process | BM
| 5.13 | Onboard employees | Hiring Manager
6 |  | OFFICE LOCATIONS
| 6.1 | Recommend office locations | CEO
| 6.2 | Board Approve office locations | Board
| 6.3 | Negotiate terms and conditions of office rentals | CEO, CFO
| 6.4 | Board to approve lease agreements
7 |  | IT
| 7.1 | Agree layout of website | CEO
| 7.2 | Design operating website: | CEO
| a) | public section
| b) | members area
| c) | secure area for Staff (board, employees, students, other)
| 7.3 | Agree responsibilities for uploading content and maintaining website | CEO
| 7.4 | Obtain quotes for development of website | CEO
| 7.5 | Agree preferred supplier | CEO
| 7.6 | Website in place | CEO
| 7.7 | Establish domain name(s) | BM
| 7.8 | Establish email facility | BM
| 7.9 | Establish user access protocols (who, what, where) | CEO
| 7.1 | Establish user ids | CEO
| 7.11 | Design Shared drive folder requirements | CEO
| 7.12 | Design Sharepoint | BM
| 7.13 | Establish videoconference facilities | BM
| 8 | POLICIES & PROCEDURES
| 8.1 | Board Policies
| 8.1.1 | Prepare Draft Policies: | CEO, BM
| a) | Board Delegations of Authority
| b) | Workplace Health and Safety Policy
| c) | Risk Management Policy
| d) | Equal Opportunity Policy
| e) | Employment Policy
| f) | Assets Policy
| g) | Travel Policy
| h) | Travel & Expenses Reimbursement Policy
| i) | Administrative Procedures policy
| j) | Foreign Exchange Policy
| k) | Investment Policy
| l) | Communications Policy
| m) | IP Policy
| n) | Accounting and revenue recognition
| o) | IT, Cyber and Access Management
| p) | Other policies
| 8.1.2 | Board approve policies | Board
| 8.1.3 | Communicate policies to staff and upload to Sharepoint | BM
| 8.2 | Management Policies & Procedures
| 8.2.1 | Prepare Draft Policies: | BM, RM, CEO
| a) | Conduct of Research Policy
| b) | Industry Engagement Guidelines
| c) | Publications Guidelines
| d) | Procedures for Conducting a Project
| e) | Presentation Guidelines & Template
| f) | Project Proposal Template & Guideline
| g) | IP Checklist
| h) | Project Leader & Lead Industry Advisor Guidelines
| 8.2.2 | Circulate to Participants for Comment | BM, CEO
| 8.2.3 | Drafts approved according to delegation | BM, RM
| 8.2.4 | Communicate policies and procedures and upload to sharepoint | BM
6 |  | MANAGEMENT COMMITTEES
| 6.1 | Research Committee
| 6.1.1 | Prepare Committee Charter and terms of reference | Chief Scientist
| 6.1.2 | Nominate committee membership and confirm | Chief Scientist, CEO
| 6.1.3 | Agree meeting frequencies | Chief Scientist
| 6.1.4 | Board to approval Committee Charter and Appointment | Board
| 6.1.5 | Provide members with committee letters to be signed | Chief Scientist
| 6.1.6 | Confirm terms of reference at first meeting | Chief Scientist
| 6.2 | Education Committee
| 6.2.1 | Prepare Committee Charter and terms of reference | Chief Scientist
| 6.2.2 | Nominate committee membership and confirm | Chief Scientist, CEO
| 6.2.3 | Agree meeting frequencies | Chief Scientist
| 6.2.4 | Board to approval Committee Charter and Appointment | Board
| 6.2.5 | Provide members with committee letters to be signed | Chief Scientist
| 6.2.6 | Confirm terms of reference at first meeting | Chief Scientist
| 6.3 | Projects and Commercialisation
| 6.3.1 | Prepare Committee Charter and terms of reference | CEO
| 6.3.2 | Nominate committee membership and confirm | CEO
| 6.3.3 | Agree meeting frequencies | CEO
| 6.3.4 | Board to approval Committee Charter and Appointment | Board
| 6.3.5 | Provide members with committee letters to be signed | CEO
| 6.3.6 | Confirm terms of reference at first meeting | CEO
|  | Note. Some CRCs establish a 'for profit' entity to manage commercialisation of CRC research. This would be established as a company with its' own board. | Chair, CEO
This document is included as a guide and is not an exhaustive list. Before using this document you should obtain appropriate independent professional advice. Last Updated February 2025.